## Sheet1
| Start | Days Duration
Planning Meeting | 2022-10-03 | 1
Design layout | 2022-10-04 | 15
Order Equipment | 2022-10-12 | 9
Initiate Trades Work | 2022-10-21 | 15
Install Workstations | 2022-10-30 | 18
Electrical Installation | 2022-10-28 | 14
Computer Installation | 2022-11-14 | 12
Debug | 2022-11-25 | 4
Training for new staff | 2022-11-29 | 5
1) highlight all the rows and columns including the titles
2) insert stacked horizontal bar chart
3) click on what to fix -> format -> format selection

## Sheet2
| Start | Days Duration
Planning Meeting | 2022-10-03 | 1
Design layout | 2022-10-04 | 15
Order Equipment | 2022-10-12 | 9
Initiate Trades Work | 2022-10-21 | 15
Install Workstations | 2022-10-30 | 18
Electrical Installation | 2022-10-28 | 14
Computer Installation | 2022-11-14 | 12
Debug | 2022-11-25 | 4
Training for new staff | 2022-11-29 | 5
1) highlight all the rows and columns including the titles
2) insert stacked horizontal bar chart
3) click on what to fix -> format -> format selection